# `

GOVERNMENT OF KHYBER PAKHTUNKHWA

SCIENCE & TECHNOLOGY AND SCIENCE & TECHNOLOGY DEPARTMENT

# Draft Revised PC-I

ICT Training for Women Empowerment

| ADP No. | Forum & Date of Approval | Total Cost |
| --- | --- | --- |
| 1157-141029 | DDWP | 30.533 Million |
| 1157-141029 | DDWP | 30.533 Million |

PREPARED BY:

DIRECTORATE OF SCIENCE & TECHNOLOGY GOVERNEMT OF KHYBER PAKTUNKHWA

# June  2020

GOVERNMENT OF KHYBER PAKHTUNKHWA

SCIENCE & TECHNOLOGY AND SCIENCE & TECHNOLOGY DEPARTMENT

| S.No | Description | Detail |
| --- | --- | --- |
| 1 | Name of the project | ICT Training for Women Empowerment |
| 2 | Location | Government of Khyber Pakhtunkhwa |
| 3 | Authorities responsible for: Sponsoring Execution Operation and maintenance Concerned Provincial Department | ST&IT Department Government of KHYBER PAKHTUNKHWA Directorate of Science & Technology, Khyber Pakhtunkhwa Directorate of Science & Technology, Khyber Pakhtunkhwa during the execution of the Project for four months. Government of Khyber Pakhtunkhwa |
|  | Proposed Commencement and Completion dates | (i) Commencement: Upon approval of project. (ii) Completion: 30-06-2020 |
| 4 | Plan provision If the project is included in the medium term/five year plan, specify actual allocation. If not included in the current plan, what warrants its inclusion and how is it now proposed to be accommodated. If the project is proposed to be financed out of block provision, indicate: iii.i) Total block provision iii.ii) Amount already committed iii.iii) Amount proposed for this project iii.iv) Balance available | The project is included in the ADP 2018-19 with allocation of Rs-10.00 Million. N/A N/A Rs. 10.000 Million |
|  | Description Of The Project Problems Statement Components of the Project | Previously the project was reflected in ADP of IT Sub-Sector due to merger of Directorate of IT into Directorate of S&T, the project has now been reflected under ADP 2018-19 in S&T Sub-Sector. Since the creation of Pakistan in 1947 Pakistan inherited the menace of poverty. The burden of this poverty was put heavily on the female population, which is 50% of the total population of Pakistan on the top of it women were neglected and under-nourished. All the governments had tried in one form or the other to develop the capacity of women on ICT but could not make a very happy progress because of various reasons. Today the present government is committed and believes in creating and enabling environment for people in general to enjoy long, healthy and creative life and for women in particular. Economic development, if it is to be meaningful and sustainable, must involve and accrue to all citizens. At the same time economic growth alone cannot guarantee social harmony, especially in an under developed societies. National development must be balanced by a strong and real emphasis on equitable distribution of development benefits especially for the lower segments of the population. This philosophy of development i.e., growth with equity is to be embodied in all national development policies. Poverty alleviation and social development has to be the central part of the overall national development. In the developing world, the menace of poverty is deep routed, especially in the rural areas while Pakistan is no exception to it. Therefore the United Nations identified the rural women as a catalyst for change if the objective of eradicating poverty is to be attained. Women are the major contributor to the agricultural labour force producing more than 50% of the developing world’s food (Food and agriculture organization). Women are actively participating in reaps, gather crops, cares for animals, plants herbs, and looks after the families but hardly ever recognized in the statistics of production while easily made a target of cultural malpractices which not only hurts her dignity but even take her life. It is very important to bring the women into the lime light so that policy makers could design their development interventions in a way that could politically and financially empower her enough to make a difference in the living conditions of herself and her family and her immediate surroundings. At the same time giving her the personal security and dignity that is her fundamental right. Today’s globalized world offers many opportunities and challenges while demonstrating the need for having a level playing field for men and women; this can only be established if we shun prejudices and isolationism. We need to explore innovative ways to overcome the formidable obstacle to the empowerment of women and gender equality. There is a need to focus and devise strategies to enhance women’s role in decision-making and power sharing in all tiers of the government. Considering the plight of women, the government of Pakistan has introduced a special hardcore poverty alleviation program focusing on the very poor families through the women of the family. The Project will help in four strategic methods to bring the women in the main stream and address the cultural barriers in the full exercise of women’s citizenship:  Awareness-raising among the citizens.  Capacity-building of women.  Training material and Manual as well as online availability of the material on Web. Within the digital divide of access to information and communication technologies (ICT) in developing countries exists another gap: between boys and girls, men and women. Particularly in developing countries and rural areas, girls and women are often restricted to traditional roles, and do not have equal access to technologies and technology training. As numerous studies have shown, when women do have access to educational resources, their Families and communities benefit. As more and more information is moving online, it is critical that women and girls have equal, safe, and reliable access to computers and the internet. Without access to computers, the internet, and technology training, girls and women will continue to be excluded from many opportunities for social and economic leadership. The women who could not read and write face various challenges with using the technology. This gap will be addressed by developing training manuals and alternate forms of communication in local language, using audiovisual materials that will help to successfully integrate these women into the program. A web portal will be developed for dissemination of information and training material to be access via computer and mobile. Equal participation of men and women in scientific research drives innovation and strengthens the economy. It is believed that diversity in science can bring together people with unique backgrounds. There is a significant role of science in society, for peace and development and the need to engage the wider public in debates on emerging scientific issues is the need of the hour. The need is to promote research partnerships with equitable gender representation and underline the importance and relevance of science in our daily lives. Pakistan is a developing country that is striving to accelerate its economic growth and catch up with the pace of the fast growing economies of the region. Women are about 48.5 % of Pakistan’s total population. Despite constituting almost half of the population, women are an underutilized talent. Women have remained somewhat under-represented in most disciplines of science and technology, and furthermore, are not well-represented at the most senior levels in all disciplines. The job options for women remain limited to agriculture, services (domestic) and small-scale industries. For achieving national development, it is an economic necessity to utilize their talents to the full at all levels of scientific and technological education, training and employment. The low socio-economic status of women in Pakistan is beginning to be recognized as a potentially significant drag on the country’s growth. No doubt, women are growing in numbers in the traditional male professions such as engineering, law, medicine, business, the police and the military. Women's ranks have also grown in the nation's entertainment, news and mass media and they are much freer than ever to express themselves in the choice of appearance, speech, clothing, arts, entertainment etc. A number of women have moved up into the executive positions. Women now make up 4.6% of board members of Pakistani companies. (Pakistani Women Breaking Stereotypes in Workplace). Top of Form The project will comprises of the following components: Training & capacity building on ICT base tools and software Training on other job oriented courses Training material (Printed, Audio/Video’s) and Manuals Advertisement/Media Awareness Women awareness program to pursue careers in science and technology Training session on inquiry based learning Online training material Enhance S&T capacity of women on S&T based business development for women. Women entrepreneurship development Trainings of school girls to pursue careers in areas of S&T i.e. Agriculture, food and nutrition Arranging training session on STEM. |
|  | Coverage | Malakand, Swat, Mansehra, Swabi, Nowshera, Dir, Kohat, D I Khan, Mardan |
| 5 | Project objectives and its relationship with sector objectives The objectives of the sector/sub sector as indicated in the medium term/three year plan be reproduced. Indicate objectives of the project and develop a linkage between the proposed project and sectoral objectives. Project Objectives Technical Objectives | E-Government was one of the major initiatives under the IT policy and Action Plan. To pursue this initiative, the Government of KHYBER PAKHTUNKHWA has initiated a large number of IT projects in different areas. One of the main objectives of the erstwhile IT Directorate was to build capacity and train the youth of the Khyber Pakhtunkhwa. To fulfill goals of development and the removal of unemployment and poverty in the Khyber Pakhtunkhwa. To impart education relevant to increased production and productivity, economic development and individual prosperity in the Khyber Pakhtunkhwa To make available skilled work force at all levels to alleviate the urban unemployment thereby helping the development of Khyber Pakhtunkhwa. To develop environmental awareness to ensure sustainable development in the Khyber Pakhtunkhwa To develop vocational aptitude, work culture, values and attitudes of the learners so as to enrich the productivity of Khyber Pakhtunkhwa. To develop entrepreneurial competencies and skills of learners for self-reliance and to undertake self-employment in the Khyber Pakhtunkhwa To develop vocational competencies, creative thinking in the related areas and facilitate training in the Khyber Pakhtunkhwa To spread awareness about different job areas and to provide backgrounds for acquiring higher level training in subjects concerned. To develop personal and humanitarian consciousness as this would help to draw out the best of their inherent abilities To provide women with vocational and job-oriented courses like Basic Computer Training and other courses To equip the women with the knowledge required to function as professionals in the industry To enhance the skill levels of women students to prepare them for employment in the ICT and BPO (Business Processes Outsourcing) industry and Science and technology To enhance capacity of women on Science and technology The Technical objectives of the project includes: Perception of ICT training by rural women: The rural women through ICT training, basic ICT skills will enhance the quality of their lives in terms of knowledge or for employment purposes. Access to Knowledge: The importance of knowledge and the ability of ICT to improve access to knowledge for work and education seemed to be well known by the female students and labor force. Economic Empowerment: ICT and trainings on S&T for women as an enabler to increase their economic empowerment in terms of earning power and position. Social Empowerment: An increase in self-confidence will be one of the most important impacts stretching across age groups and occupational status. Train women with the vital living skills in order for them to take a dynamic role in their societies through integrating ICT, science & technology into all aspects of life. Empower women through ICT training and training on science and technology on legal issues, non-violence, political participation and civic education. Organize activities that support educational, economic and political development. |
| 6 | Description, technical parameters, technology transfer aspects, features of system, justification, benefits, required equipment and physical infrastructure: Description of proposed system Justification of Proposed System Features of the proposed system D. Justification of Revision Provide details of equipment, machinery required for the project. Provide detail of physical infrastructure required for the project Indicate governance issues of the sector relevant to the project and strategy to resolve them. | Computer education is playing a key role in every field of life. With education in cities laying emphasis on computer education and literacy, the educational institutions for girls in small cities are lagging behind. The Project is trying to provide a solution to this problem. By making computer education to girls we are promoting that there be no gender discrimination but empowerment of girls and women for a better life. Girls are as keen learn these new technologies but are unavailable as they are unable to access cyber cafes or computer institutes and also because of the presence of men and boys. Belonging to conservative and illiterate parents, they are not allowed due to privacy and security reasons. The other very important factor is financial constraint which makes the parents reluctant to invest too much in education believing that the girls only have to be married off. The promotion of micro and small-scale enterprises (MSEs) has been recognized as an important strategy for advancing the economic empowerment of women while reducing poverty and gender inequality. Small business is engines of growth and considered a backbone for economic expansion by many governments. At the household level, Women’s microenterprises and small subsistence business play a crucial role in ensuring the survival of poor households, and in building up women’s confidence, skills and socioeconomic status with social benefits accruing to the community and future generations. Many institutional and regional players promote them as part of a developmental strategy to create jobs in developing countries, generate employment opportunities for the poor in rural areas and populations unreached by the formal economy, and to drive innovation. Women entrepreneurs are offered new opportunities by ICT’s to start and grow businesses. Furthermore, the women and girls will get employment and will provide edge in the employment. Training / Capacity Building The main aim of the project is to empower the women and girls of the urban and semi urban areas of the province through ICT training. The audience will be educated women in any field of sciences or social sciences or middle level educated women. The courses will be designed in such a manner so that the training may help them in job seeking and self-employment. The proposed areas of training will be: Computer Basic training It will help in seeking jobs in the field of data entry, computer operator, office assistant, Airline Ticketing reservation and surveys Internet usage, email and online surfing It will help to communicate with relatives and valuable Clients other areas and educating them self’s on different trades and promotion of regional products and services. Office Automation It will help in seeking jobs in the field of data entry, computer operator, office assistant, Airline Ticketing reservation and surveys Website Development and e- commerce This Course will help in self-employment and the students will be able to develop small-scale websites and market the regional products and services globally. Coral Draw and Graphic designing & Logo design This Course will help in self-employment and the students will be able to create logo’s, broachers and other printing materials. Search engine Optimization, Directory services and Advertisements This course will help in self-employment and can earn handsome amount by getting online business regarding search engine optimization and directory services. Accounting applications This course will help the students to learn and maintain the accounts of an organization, which will help them in job seeking. Provide model of self-sustainability of the project A sustainability model will be developed during the execution of the project for continuation of the activity. Training on Science & technology Attached at Annex -III Note: The above training have been completed and new training are mentioned at Annexure-V As Directorate of IT previously executed this project, which has been merged with Directorate of Science & Technology and the scheme has been reflected in the ADP of S&T Sub-sector. Therefore, the scope of the scheme has been changed as activities related to the field of science has been included in the PC-I N/A The physical infrastructure needed for the project was computer labs which were provided by the Elementary & Secondary education department. List of schools and provision of female IT teachers district wise is attached at Annexure -IV N/A |
| 7 | Cost estimates a) Indicate date of estimation of Project cost. Basis of determining the capital cost be provided. It includes market survey, schedule rates, estimation on the basis of previous work done etc. | December 2018 N/A |
| 8 | Annual operating and maintenance cost after completion of the project: (Item-wise annual operating cost) | N/A |
|  | Implementation Methodology Sustainability: Socio cultural & economic sustainability | Step 1: The services of consultant and/or partner organization will be hired to impart trainings ICT and technology based to women. Subsequently, advertisement will be made to identify the women/girls interested in learning computer education. Advertisements will be make in the daily newspapers as well, other than this Panaflex will be displayed at the schools where the training program will be held and at the training centers of the Social welfare department in the respective Districts. An orientation of the training plan, design a curriculum will share with all the stakeholders. Step 2: An organization with the requisite experience will be selected through Open Bidding /Tendering through Departmental Consultant Selection Committee. Step 3: Girls and women of the selective districts will be enrolled in the program. In 4th Step the training schedules and contents will be finalized and training will be held In 5th Step video/Audio training materials will be developed and will be published on the Web site for later usability. Step 5: Certificates will be issued to the successful candidates All the trainings related activities with broadened scope with inclusion of science, technology, innovation and entrepreneurship would be managed by the consultant and/or partner organization. The behavioral and attitudinal changes brought in by the project among the local communities particularly the girls and women will empower them to actively participate in decision making in all other future activities. Women and girls will come together on a common platform to discuss their socio cultural problems bringing changes in age-old social habits. The project will significantly affect the lives of these women after completing the computer course and of the young girls who got the opportunity to be an instructor at the institute. This would bring about the much-needed confidence among them helping them move forward towards development. Their active participation in the decision making process, community based planning and being an instructor will bring about ownership of the project. |
| 10 | Financial plan and mode of financing: a) Equity: Indicate the amount of equity to be financed from each source: Sponsors own resources Federal government Provincial government DFI's/banks General public Foreign equity NGO’s/beneficiaries Others b) Debt Indicate the local & foreign debt, interest rate, grace period and repayment period for each loan separately. The loan repayment schedule be also annexed. Grants along with sources Weighted cost of capital | ADP 2018-19 N/A N/A |
| 11 | Benefits of the project: Direct and indirect Employment generation (direct and indirect) Environmental impact | Social and economic empowerment of the women Employment opportunities Self confidence of women in male dominated society The program will create awareness among the masses regarding the girls education Women will be able to access information regarding Health care and child care through internet Technological empowerment of the women Political empowerment of the women Socio-economic development of the region Women will be able to market local products and services One position of assistant project coordinator was created through PC-I and indirectly women will be empowered and will be able to get desk jobs in the market and will promote self-employment opportunities. Project will have Positive impact on the environment. |
| 12 | Implementation schedule (Indicate starting and completion date of the project) | The project will be started after the approval from DDWP and has to be completed in one Year. The sequence of activities for execution of this project, after issuance of administrative approval for the project, will be as follows: (i) Preparation of criteria for the selection of training firms After the Approval of PC-1 (ii) Evaluation & award of contracts for S. No. (i) above One Month after the tender process (iii) Advertisement for selection students in the respective Districts 15 days after award of contract at No.(ii) (iv) Selection of student One Month after Advertisement at No.(iii) (v) Development of web portal for the project 1 Months after Advertisement web portal developed. (iii) (vi) Training at the selected schools 15 Days after S.No.(iv) (x) Implementation 8 Months |
|  | Risk Analysis | S.No Risk Mitigation 1 There is a risk of non enrolment in the courses An advertisement will be made in the print media for awareness of the women to participate in the program. 2 There is a risk of non availability of internet at the schools Provision has been kept for the installation of the internet at the schools where internet will not present. 3 There is a risk of non availability of female IT trainees at the areas where training will be scheduled. The training will be outsourced to the firm and the availability of trainees will be responsibility of the Firm at all location. 4 There is a risk of stoppage of the activity after completion of the Project. A methodology will be devised during the execution of the project for self sustainability of the activity. Keeping in view the importance of the project it is proposed to run the activities of scheme on a sustainable manner. 5 There is a risk of non cooperation of the school administration during the program The management of E&SE Department will be kept on board before utilization of the school premises. 6 There is a risk of hardware problems in the schools labs Provision of maintenance of Hardware has been kept in PC-I and will utilized if necessary 7 There is risk of non proper execution of the project at district level. A proper monitoring team will be formulated comprises of the ADO female of the concern district for monitoring purpose. |
| 13 | Manpower requirements: The manpower requirements by skills during execution and operation of the project be provided. | One Assistant Project Coordinator has been hired who is looking after the project matters. |

|  | Sign of: Prepared by: Reviewed By: Checked by: I Approved by: | Miss. Saba Gul Assistant Project Coordinator ICT Training for Women Empowerment ____________________ Mr. Wiqar Ahmad Assistant Director ST, Directorate of ST,Govt. of KP __________________________ Mr. Bilal Jabbar Additional Director, Directorate of Science & Technology Govt. of Khyber Pakhtunkhwa _________________ Dr. Khalid khan Director-ST, Directorate of ST, Govt. of KPK _____________________ In-charge Planning Cell, ST&IT Department, Govt. of KP _________________________ Mr. Zafar Iqbal Secretary to Government of Khyber Pakhtunkhwa, ST&IT Department |
| --- | --- | --- |

Annexure -I

SUMMARY OF THE COST ESTIMATE

| S. No | Description | Previous | New proposed | Total |
| --- | --- | --- | --- | --- |
| 1 | Training /Capacity building | 18.06 | 7.182 | 25.242 |
| 2 | Human Resource | 0.765 | 2.304 | 3.069 |
| 3 | Hardware (Laptop and printer for Assistant Project Coordinator) | 0.199 | 0.000 | 0.199 |
| 4 | Operational Cost | 1.328 | 0.695 | 2.023 |
|  | Total: | 20.352 | 10.182 | 30.533 |

For Detail see annexure VI

Annexure -II

Human Resource

| S.No | Description | BPS | Previously Approved | Newly Proposed |
| --- | --- | --- | --- | --- |
|  |  |  | No | Salary /Month | No of Months | Total | No | Salary /Month | Annual Salary | No of Months | Total |
| 1 | Asst: Project Coordinator | 16 | 1 | 60,000 | 12 | 720,000 | 1 | 60,000 | 720,000 | 12 | 720,000 |
| 2 | Naib Qasid | 04 | 0 | 0 | 0 | 0 | 2 | 16000 | 384,000 | 12 | 384,000 |
| 3 | Stipend for Internees (04 Females)_ | 0 | 0 | 0 | 0 | 0 | 4 | 25,000 | 1200,000 | 12 | 1200,000 |
| Total | 720,000 |  | 2304000 |

| ICT Training for Women Empowerment |
| --- |
| Total number of students trained |
| S. No | School Name | District | Batch 1 | Batch 2 | Total Students |
| 1 | GGCMHS Charsadda | Charsadda | 66 | 62 | 128 |
| 2 | GGHS Dher (Julagram | Malakand | 0 | 120 | 120 |
| 3 | GGHS Meherdi | Malakand | 40 | - | 40 |
| 4 | GGHS Bagdada No.1 | Mardan | 81 | 58 | 139 |
| 5 | GGHSS Nowshera Kalan | Nowshera | 88 | 77 | 165 |
| 6 | GGHSS Shaidu | Nowshera | 106 | 93 | 199 |
| 7 | GGHS DAGAI | Swabi | 105 | 100 | 205 |
| 8 | GGHS Karnal Sher Killi (Jamal Abad) | Swabi | 123 | 121 | 244 |
| 9 | GGHSS KALU KHAN | Swabi | 145 | 120 | 265 |
| 10 | GGHSS Kotha | Swabi | 114 | 103 | 217 |
| 11 | GGCMHSS S/Sharif No.1 For Girls | Swat | 116 | 60 | 176 |
| 12 | GGHSS Manglowar | Swat | 138 | 87 | 225 |
| Total | 1122 | 1001 | 2123 |

Annexure –III

List of Schools where Computer Labs has been established

| S.No | District | Tehsil | Location | School Code | School name | Village Name | Computer Lab Exists | No. of Computers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SWABI | Swabi | Rural | 36282 | GGHSS KALABAT | Kalabat | Yes | 18 |
|  | SWABI | Lahor | Rural | 36693 | GGHSS LAHOR | Lahor | Yes | 0 |
|  | SWABI | Swabi | Rural | 34468 | GGHSS Baja | Baja |  |  |
|  | SWABI | Swabi | Rural | 34480 | GGHSS Shah Mansoor | Shah Mansoor |  |  |
|  | SWABI | Swabi | Rural | 36287 | GGHSS Shewa | SHEWA |  |  |
|  | SWABI | Swabi | Rural | 36692 | GGHSS KALU KHAN | Kalu Khan |  |  |
|  | SWABI | Topi | Urban | 36691 | GGHSS Topi | TOPI |  |  |
|  | SWABI | Topi | Rural | 36283 | GGHSS Kotha | Kotha |  |  |
|  | SWAT | Babozai Swat | Rural | 36700 | GGHSS Udigram | ODIGRAM MINGORA | Yes |  |
|  | SWAT | Kabal | Rural | 36325 | GGHSS Kabal | KABAL | Yes |  |
|  | SWAT | Matta | Rural | 36701 | GGHSS Matta | MATTA | Yes |  |
|  | SWAT | Babozai Swat | Urban | 36316 | GGCMHSS S/Sharif No.1 For Girls | SAIDU SHARIF |  |  |
|  | SWAT | Babozai Swat | Rural | 36329 | GGHSS Manglowar | MANGLOOR |  |  |
|  | DIR PAYAN | Temargara | Urban | 36702 | GGCMHSS TIMERGARA | TIMERGARA | Yes | 16 |
|  | DIR PAYAN | Temargara | Rural | 36345 | GGHSS ZIARAT TALASH | ZIARAT TALASH | Yes | 0 |
|  | DIR PAYAN | Samarbagh | Rural | 36346 | GGHSS SAMARBAGH | SAMAR BAGH |  |  |
|  | DIR PAYAN | Adenzai | Rural | 36343 | GGHSS OUCH | OUCH |  |  |
|  | DIR PAYAN | Lal Qala | Rural | 36339 | GGHSS KUMBAR | KUMBAR |  |  |
|  | DIR PAYAN | Samarbagh | Rural | 36347 | GGHSS MAYAR JANDOL | MAYAR |  |  |
|  | DIR PAYAN | Balambat | Rural | 36336 | GGHSS RABBAT | RABAT |  |  |
|  | KOHAT | Kohat | Rural | 36708 | GGHSS BABRI BANDA | BABRI BANDA | Yes |  |
|  | KOHAT | Lachi | Rural | 36377 | GGHSS SHAKARDARA | SHAKAR DARA |  |  |
|  | KOHAT | Kohat | Rural | 36707 | GGHSS JUNGLE KHEL | JUNGLE KHEL |  |  |
|  | KOHAT | Kohat | Rural | 36374 | GGHSS BILITANG | BILITANG |  |  |
|  | KOHAT | Kohat | Rural | 36378 | GGHSS GUMBAT | GUMBAT |  |  |
|  | KOHAT | Lachi | Rural | 36709 | GGHSS LACHI | LACHI |  |  |
|  | MALAKAND | Dargai | Rural | 36710 | GGHSS Sakhakot | SAKHAKOT | Yes | 16 |
|  | MALAKAND | Dargai | Rural | 36391 | GGHSS Koper | KOPER |  |  |
|  | MANSEHRA | Mansehra | Urban | 36480 | GGHSS No.2 Mansehra | MANSHERA |  |  |
|  | MANSEHRA | Mansehra | Rural | 36465 | GGHSS BEHALI | BEHALI |  |  |
|  | MANSEHRA | Mansehra | Rural | 36478 | GGHSS Lassan Nawab | LASSAN NAWAB |  |  |
|  | MANSEHRA | Mansehra | Rural | 36482 | GGHS Perhanna | Perhanna |  |  |
|  | MANSEHRA | Mansehra | Rural | 36483 | GGHSS PHULRA | PHULRA |  |  |
|  | MANSEHRA | Oghi | Rural | 36484 | GGHSS SHERGHAR | SHERGARH |  |  |
|  | MANSEHRA | Oghi | Rural | 36724 | GGHSS OGHI | OGHI |  |  |
|  | NOWSHERA | Nowshera | Rural | 36737 | GGHSS Pir Pai | PIR PAI | Yes | 16 |
|  | NOWSHERA | Nowshera | Urban | 36736 | GGHSS Shaidu | SHAIDU | Yes | 16 |
|  | NOWSHERA | Nowshera | Urban | 36734 | GGHSS Akora Khattak | AKORA KHATTAK | Yes |  |
|  | NOWSHERA | Nowshera | Urban | 36735 | GGHSS Nowshera Kalan | NOWSHERA KALAN |  |  |
|  | NOWSHERA | Nowshera | Rural | 36533 | GGHSS Dag isamil Khel | DI KHEL |  |  |
|  | NOWSHERA | Nowshera | Rural | 36536 | GGHSS Khair Abad | KHAIR ABAD |  |  |
|  | NOWSHERA | Nowshera | Rural | 36540 | GGHSS Rashakai | RASHAKAI |  |  |
|  | D.I.KHAN | DIKHAN | Urban | 36714 | GGHSS NO. 2 KIRI ALIZAI | MOHALLAH KIRI ALIZAI |  |  |
|  | D.I.KHAN | KULACHI | Urban | 36407 | GGHSS KULACHI | KULACHI | Yes | 16 |
|  | D.I.KHAN | PAHARPUR | Rural | 36409 | GGHSS PANIALA | PANIALA | Yes | 16 |
|  | D.I.KHAN | PAHARPUR | Rural | 36715 | GGHSS PAHARPUR | PAHARPUR | Yes | 16 |
|  | D.I.KHAN | DIKHAN | Urban | 36401 | GGCMHSS NO. 6 CHAH SYED MUNAWAR | CHAH SYED MUNAWAR | Yes | 14 |
|  | D.I.KHAN | PAHARPUR | Rural | 34850 | GGHSS MITHA PUR | MITHAPUR |  |  |
|  | D.I.KHAN | DIKHAN | Urban | 36400 | GGHSS NO. 5 QASABAN | MOHALLAH QASABAN |  |  |
|  | D.I.KHAN | PAROA | Rural | 36410 | GGHSS PAROA | PAROA |  |  |
|  | D.I.KHAN | DIKHAN | Urban | 36404 | GGHSS NO. 9 DINPUR | DIN PUR |  |  |
|  | D.I.KHAN | PAHARPUR | Rural | 34851 | GGHSS BILOT SHARIF | BILOT SHAIF |  |  |
|  | DIR BALA | Dir | Urban | 36690 | GGHSS Dir | Dir | Yes | 16 |
|  | DIR BALA | Barawal | Rural | 36270 | GGHSS Brawal | Brawal |  |  |

Annexure-IV

Human Resource

| Sr. # | Designation | No. of Post | Responsibilities | Qualification/ Experience |
| --- | --- | --- | --- | --- |
| 1. | Assistant project Coordinator BPS-16 | 01 | The Assistant Project Coordinator will be responsible for the overall management of the Project, staff and Activities in the project which will include communication, reporting, monitoring and other task during the execution of the project. | MBA- HR/BBA-HR /master in Social Sciences With one year post qualification experience in the field of training and capacity building. Must have experience in well reputed Public or Private sector organization. |
| 2 | Naib Qasid BPS (03) | 02 | Duties as per Govt. rules and any extra duty assigned | Literate/ No prior experience required Age 20-35 years (age relaxation as per Govt. rules |

Annexure- V

EXPENDITURE INCURRED ON ICT TRAININGS

| S.NO | COURSE TITLE | DURATION | Number of batches | Course fee per candidate | No of expected candidates. | Total Training Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Computer Basic Training | 3 Months | 4 | 3000 | 1000 | 3000000 |
| 2 | Software Installation & Trouble Shooting | 3 Months | 4 | 3000 | 500 | 1500000 |
| 3 | Internet usage, email and Social Media | 3 Months | 4 | 3000 | 800 | 2400000 |
| 4 | Office Automation | 6 Months | 2 | 7000 | 500 | 3500000 |
| 5 | Website Development and e-commerce | 6 Months | 2 | 8000 | 210 | 1680000 |
| 6 | Coral Draw and Graphic designing & Logo design | 6 Months | 2 | 8000 | 100 | 800000 |
| 7 | Search engine Optimization, Directory services and Advertisement services | 6 Months | 2 | 10000 | 150 | 1500000 |
| 8 | Accounting applications | 6 Months | 2 | 8000 | 100 | 800000 |
| 9 | Mobile Application development | 6 Months | 2 | 20,000 | 80 | 1600000 |
| 10 | Software Development | 6 Months | 2 | 30,000 | 70 | 2100000 |
| Total |  | 18880000 |
| Total in Million |  | 18.89 |

Annexure- VI

EXPENDITURE ON NEW PROPOSED TRAINING ON ICT & SCIENCE & TECHNOLOGY

| S.NO | COURSE TITLE | DURATION | Number of batches | Course fee per candidate | Expected no of Candidates | Total Training Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Computer Basic Training | 3 Months | 1 | 3000 | 700 | 2,100,000 |
| 2 | Internet usage, email and Social Media | 3 Months | 1 | 3000 | 600 | 1,800,000 |
| 3 | Trainings on S&T based business development for women | 3 Months | 1 | 3000 | 600 | 1,800,000 |
| 4 | Women empowerment through transfer of technology i.e. Food preservation including fruits and vegetables using latest technologies developed e.g. mushroom for earning livelihood in off seasons, To train women on agricultural related technologies Train women on the use of technologies used in the making of handy crafts Any other training required for the empowerment of women on technologies & entrepreneurship | 3 Month | 1 | 3000 | 494 | 1,482,000 |
| `Total |  | 7,182,000 |
| Total in Million |  | 7.182 |

PROPOSED METHODOLOGY FOR SELECTION OF CONSULTANT

| S.NO | COURSE TITLE | Education required for trainings |
| --- | --- | --- |
| 1 | Computer Basic Training | Higher Level Secondary Level Graduate Level |
| 2 | Internet usage, email and Social Media |  |
| 3 | Trainings on S&T based business development for women |  |
| 4 | Women empowerment through transfer of technology i.e. Food preservation including fruits and vegetables using latest technologies developed e.g. mushroom for earning livelihood in off seasons, etc To train women on agricultural related technologies Train women on the use of technologies used in the making of handy crafts Any other training required for the empowerment of women on technologies |  |

Expenditure made in the Project

|  | Description | Allocation | Expenditure |
| --- | --- | --- | --- |
| S.No |  |  | Year 2015-16 | Year 2016-17 | Year 2017-18 | New Proposed Year 2018-19 (Rs. In million) |
| 1 | Human Resource | 3.069 | 0 | 175,000 | 590,000 | 2.304 |
| 2 | Training /Capacity Building | 25.242 | 2,300,000 | 15,762,688 | 0 | 7.182 |
| 3 | Hardware | 0.2 | 199,000 | 0 | 0 | 0.000 |
| 4 | DSL/Internet | 0.120 | 0 | 62,000 | 51,000 | 0.000 |
| 5 | Stationary | 0.200 | 0 | 97,057 | 82,943 | 0.0267 |
| 6 | Advertisement | 1.00 | 0 | 422,415 | 269,114 | 0.309 |
| 7 | Office Renovation | - | 0 | 0 | 0 | 0.000 |
| 8 | Others (Contingences) | 0.200 | 0 | 0 | 150,000 | 0.050 |
| 09 | Electricity | 0.001 | 0 | 0 | 0 | 0.000 |
| 10 | Telephone | 0.001 | 0 | 0 | 0 | 0.000 |
| 11 | TA/DA | 0.300 | 0 | 102,390 | 81,700 | 0.116 |
| 12 | Postage | - | 0 | 0 | 0 | 0.000 |
| 13 | Entertainment | - | 0 | 0 | 0 | 0.000 |
| 14 | Hardware Maintenance | 0.001 | 0 | 0 | 0 | 0.000 |
| 15 | Workshops, Seminars | 0.200 | 0 | 0 | 0 | 0.200 |
| 16 | Total | 30.533 | 2,499,000 | 16,621,550 | 1,224,757 | 10.188 |
|  | Grand Total | 30.533 |

# Comments

Make it 6 months and double the number of internees and also include 2 N/Qs

# Text boxes

Social 
empowerment

Political 
empowerment

Technological 
empowerment

Psychological 
empowerment

New knowledge and information

Awareness and understanding of issues

Skills, abilities and competence

Support.

Training and Capacity Building

Having a voice and being listened to

Participating in policy making

Through ICT and Social Media

Education and access to information through Social Media

Knowledge about ICTs, technologies, entrepreneurship

Awareness and understanding about ICTs

Skills and competence in using new ICTs

Ongoing support and advice in using ICTs

Access to high quality technologies

Confidence to use and speak about ICTs

Self-confidence and self-esteem

Feeling more valued and respected

Motivation, interest and enthusiasm

Freedom to do things or express yourself

Feelings of belonging

Wellbeing and happiness

Advertisement /Media Campaign

Application

Selection

Enrolment

Consultant firm selection for Training

Content Development

Training Scheduling

Training Program

Computer Labs of E&SE Department

Provision of Trainers at Each Location

Monitoring