GOVERNMENT OF KHYBER PAKHTUNKHWA

SCIENCE & TECHNOLOGY AND

INFORMATION TECHNOLOGY DEPARTMENT

# Establishment of Model Science Labs in Merged Districts

# PC-1

| ADP No. | Forum & Date of Approval | Total Cost |
| --- | --- | --- |
| 921-190249 | DDWP | Rs: 23.873 Million |
|  | Dated: | February 2020 |
|  | Total Duration | 12 Months |

PREPARED BY:

DIRECTORATE OF SCIENCE & TECHNOLOGY

GOVERNMENT OF KHYBER PAKHTUNKHWA

February 2020

GOVERNMENT OF KHYBER PAKHTUNKHWA

SCIENCE & TECHNOLOGY AND INFORMATION TECHNOLOGY DEPARTMENT

| S.No | Description | Detail |
| --- | --- | --- |
| 1 | Name of the project | Establishment of Model Science Labs in Merged Districts |
| 2 | Location | Merged Districts |
| 3 | Authorities responsible for: Sponsoring Execution Operation and maintenance | ST&IT Department, Government of Khyber Pakhtunkhwa Directorate of Science & Technology. Directorate of Science & Technology |
| 4 | Plan provision If the project is included in the medium term/five year plan, specify actual allocation. If not included in the current plan, what warrants its inclusion and how is it now proposed to be accommodated. If the project is proposed to be financed out of block provision, indicate: iii.i) Total block provision iii.ii) Amount already committed iii.iii) Amount proposed for this project iii.iv) Balance available Provision in the current year ADP 2019-20 | N/A N/A N/A The scheme has been reflected into ADP 2019-20 with the total cost of 20 Million with an allocation of Rs. 4.994 Million for the current fiscal year 2019-20 |
| 5 | Project objectives and its relationship with sector objectives The objectives of the sector/sub sector as indicated in the medium term/three year plan be reproduced. Indicate objectives of the project and develop a linkage between the proposed project and sectoral objectives. | The economic order in developing countries like Pakistan is changing in the wake of two unprecedented challenges – globalization and emergence of knowledge-based economies. Instead of relying on financial resources, knowledge-based economies rely on the intellectual capital. Investment in increasing the quality and quantity of knowledge will in turn enable indigenous development in Science & Technology sector while offering quality services at lower costs. Pakistan like many other developing Muslim countries faces three major developmental challenges: 1) the increase of macro-productivity of the economy; 2) liberalizing trade and encouraging foreign investments; 3) government policies must support the shift towards knowledge-based economy. The challenge is to link the economy with knowledge, and to set guidelines for this linkage. OBJECTIVES OF THE PROJECT: To establish model Science Labs in Merged Districts (01 Each) To strengthen students for scientific temper, emerge as a progressive and enlightened society. To provide leadership in organizing science labs on proper scientific lines, rationalize the distribution of lab gear; improve the monitoring and utility of lab gear to improve scientific and technical attitude of the students and teachers. Initiate a dialogue on reviewing the lab education system and align it with market demand. To assist in scientific procedures and make them more ground reality based. Through the initiative attract the brightest young students to careers in science and technology, by conveying a sense of excitement concerning the advancing frontiers. To provide students with inquisitive skills to work on their ideas in the labs ranging from ideas realizing to solving real world problems |
| 6 | Description, technical parameters, technology transfer aspects, required equipment and physical infrastructure: Describe the project and indicate existing facilities in the area and summary of total cost Provide technical parameters i.e. input and output of the project. Also discuss technological aspect of the project. MOU | Education is one of the major sectors where Science and Technology can play a valuable role in order to give a scientific touch to the Masterminds of the nation at lower and middle levels. DoST feels obligated to assist all relevant institutions where issues and problems regarding science cause the retardation in building a scientific society. DoST has planned to mobilize scientists and research institutions to co-operate in programmed towards the development of school Science lab teaching. Therefore, as part of the efforts to improve lab education in Khyber Pakhtunkhwa all relevant and interested organizations and institutions will be approached for technical and financial partnership/assistance/support for a national cause. The program is based on demonstrating the importance of practical work in teaching of science, through capacity building of the labs in selected school, thereby bridging the gap between science as practiced and science in schools. The project is also aimed at fostering the development of scientific-reasoning and problem-solving skills based on experimentation and evidence evaluation in daily life. It is hoped that more use of experimentation in schools, a culture of scientific investigation and literacy will be developed, leading ultimately to increased production of new scientific knowledge in Khyber Pakhtunkhwa. Through the initiative model labs will be established, invigorated and strengthened through provision of required equipment, lab gear, renovation, audio visual support in repair of existing equipment and human resource development ensuring that precious government funds spent in establishing the labs are mobilized in the best interest of the public service. Model labs will also be established to demonstrate how to organize a lab on proper scientific lines. It is now an established fact that there is very little knowledge in terms of how to organize a lab, how should the lab be utilized as a learning place for students, how to make it interesting for the students, how to arouse the curiosity and critical thinking of the students. Good laboratory design in schools involves the science department from the outset and ensures that teaching and learning is central to the design process. The practical experience of science teachers and technicians can also help avoid costly mistakes in both design and fitting out. Efforts will be made to improve the standardized design of the lab. Safety measures checklist for Teachers and Students has been proposed (annexed) for provision of healthy and safe enbvironment during practical activities in the lab. At current, the merged areas districts were badly affected through War on terrorism which has indirectly ruined the education systems with in standards. The project envisages Establishing 07 model labs, 1 each in all merged districts of Khyber Pakhtunkhwa based on need assessment exercised carried out. The schools will be selected through mutually agreed criteria with Directorate of Education Merged Area Secreatriat. It is presumed that the building will be present but necessary modifications will be made (ceiling, carpeting, electrification etc as per requirement in the model lab). The initiative intends to promote the concept of institutionalizing the development and production of low cost/no cost material and lab gear at local level and gradually decrease dependence on import. It will be ensured that the use of new technology to facilitate learning. Computers are used to record details & for mathematical calculations, video to record on interactive board & play back science experiments and syllabus work demonstration before proceeding with chemicals. So it will be easily use as a hand held for on the spot recording of work. So this technology will also use as a notes or handbook of teacher on spot lab teaching expertise. Necessary capacity building programs will be designed for all science teachers and science students to enhance science & mathematics teaching to boost students’ achievements in Science & Math’s to provide rich learning experience for students. Much of this standard is acknowledged as critical, even if unavailable, for students in secondary schools. It must be emphasized, however, that this standard applies to the entire science program and all students in all grades. In addition, this standard demands quality resources that often are lacking and seem unattainable in most of the schools or districts. But missing resources must not be an excuse for not teaching science. Many teachers and schools "make do" or improvise under difficult circumstances (e.g., crowded classrooms, time borrowed from other subjects, and materials purchased with personal funds). Establish 7 model labs, 1 each in all merged districts of Khyber Pakhtunkhwa. Strengthen selected secondary/ higher secondary school lab/ multipurpose labs/ throughout Khyber Pakhtunkhwa especially with a view that the labs be open to students with abilities to work in the labs Provide educational aids for ‘science education through learning by doing’ Low cost/ no cost material development and transfer of know how to utilize their skills. Carrying out a study on assessment of lab gear requirement per student per year Carry out need assessment exercise as part of the establishment of model lab Experimentation of lab teaching techniques in selected schools Facilitate visits of the students to academically relevant institutions/ organizations Prepare and disseminate guidelines and checklist for organizing a lab on proper scientific lines Prepare and disseminate videos of practicals of the secondary/higher secondary school syllabus Organize workshops, seminars, symposia, exhibition etc on the importance of lab teaching in education Conduct visits & training of all science teachers & students of the entire district to the model lab ANNEXURE – I MOU has been signed with Directorate of Education (Merged Areas) for Establishment of Science Labs. ANNEXURE – X |
| 7 | Cost estimates a) Indicate date of estimation of Project cost. Basis of determining the capital cost be provided. It includes market survey, schedule rates, estimation on the basis of previous work done etc. b) In case of revised projects, provide: History of project approval, cost and ADP number. Item-wise, year-wise actual expenditure and Physical progress done. Provide revised year-wise estimation of physical activities and cost. | JULY 2019 The costing has been done through market survey and on previous work done. N/A N/A N/A |
| 8 | Annual operating and maintenance cost after completion of the project: (Item-wise annual operating cost) | Annual Recurring Charges after the completion of project is approximate 15.00 Million |
| 9 | Vehicle | 01 vehicle is required for the project staff visit across the Province |
| 10 | Financial plan and mode of financing: a) Equity: Indicate the amount of equity to be financed from each source : Sponsors own resources Federal government Provincial government DFI's/banks General public Foreign equity NGO’s/beneficiaries Others b) Debt Indicate the local & foreign debt, interest rate and grace period and repayment period for each loan separately. The loan repayment schedule is also annexed. Grants along with sources Weighted cost of capital | The project will be completely financed by Provincial Government of Khyber Pakhtunkhwa) N/A |
| 11 | Benefits of the project: Employment generation (direct and indirect) Environmental impact | Financial There will be no direct financial benefit to the government at least in the short term. Through the competition government would invest in the students for production of future scientists and technologists. Social benefits with indicators Students and their teachers would be engaged in healthy activities Increased awareness among the students about the importance of S&T education Employment generation (direct and indirect) The project will generate reasonable direct employment i.e. project staff and will trigger a chain of activities in which material supplier, labor etc would be engaged. Environmental impact It sure will have positive impact on environment. Student will be made aware of environment around them and how to protect it. Impact of delays on project cost and viability Delays in fund release and in response of relevant departments could lead to cost escalation but will have little impact on the viability of the project at least short term |
| 11 | Implementation schedule (Indicate starting and completion date of the project) Implementation Methodology | (i) Date of Start: (ii) Date of Completion: SEE ANNEXURE |
| 12 | Management structure and manpower requirements: Administrative arrangements for implementation of project. The manpower requirements by skills during execution and operation of the project are provided. Detail job description of Man Power required Justification for increase in salaries of the current working staff Justification of new staff required | The Project will be implemented under the overall supervision of Directorate of Science and Technology. Within 1 to 2 months after the approval of the project See Annexure - VI |
| 13 | Miscellaneous items required for the project Summary of Total Cost | See Annexure - (detailed cost estimation) Annexure I |
| 14 14 | Review Committee Sign In Prepared by: Reviwed by: Forwarded by: iv. Checked by: v. Approved by: | The following high-level Project Steering Committee will review the performance of the project. Director – S&T Additional Director- S&T Representative of ST&IT Department Representative of Directorate of Education Merged Areas. _______________________ Mr. Zia Ullah Khan, Manager Networks/Systems ____________________ Mr. Bilal Jabbar, Additional Director _____________________ Dr. Khalid Khan, Director(S&T) _______________________ Mr. Abdul Basit, Chief Planning Officer, ST&IT Department. _________________________ Mr. Zaffar Iqbal, Secretary to Government of Khyber Pakhtunkhwa, ST&IT Department. |

ANNEXURES

Annexure – I

| SUMMARY OF TOTAL COST FOR 07 MODEL SCIENCE LABS |
| --- |
| S.No | Description | Total Cost (in Rs) | Total Cost (In Million) |
| 1 | Equipment for Model Science Labs | 4,362,813.00 | 4.363 |
| 2 | Hardware | 2,800,000 | 2.800 |
| 3 | Furniture/Renovation | 8050000 | 8.050 |
| 4 | Operational Expenditure | 3400000 | 3.400 |
| 5 | Human Resource | 3060000 | 3.06 |
| 6 | Vehicle | 2,200,000 | 2.200 |
|  | Total Cost | 23872813 | 23.873 |

Annexure – II

| HARDWARE EQUIPMENT |
| --- |
| S.No | Description | Unit Price | Qty | Total Cost | Total Cost (In Million) |
| 1 | Multimedia Projector | 100,000 | 07 | 700,000 | 0.700 |
| 2 | Desktop Computer with UPS | 100,000 | 07 | 700,000 | 0.700 |
| 3 | Laser Jet Printer | 50,000 | 07 | 350,000 | 0.350 |
| 4 | Other Necessary items | 150,000 | 07 | 1050,000 | 1.050 |
|  | Sub Total |  |  | 2800000 | 2.8 |
|  | Total Cost for 07 Model Science Labs |  | 7 | 2,800,000 | 2.800 |

Annexure – III

| FURNITURE |
| --- |
| S.No | Description | Unit Price | Qty | Total Cost | Total Cost in Million |
| 1 | Lab Renovation (1. Renovation of lab Room (Aprox size: 30x20 Avg) includes a. Ceiling b. Flooring c. Verticle Blinds d. Wall cabinets e. Tables f.Paint g. Sink h. Electrification i. Inauguration plates j. Branding of Model Science Lab | 1,000,000 | 1 | 1,000,000 | 1.000 |
| 2 | Chairs / Stools | 5,000 | 20 | 100,000 | 0.100 |
| 3 | Other Necessary furniture Items | 50,000 | 1 | 50,000 | 0.050 |
|  | Sub Total |  |  | 1,150,000 | 1.150 |
|  | Total for 07 Model Science Labs |  | 7 | 8050000 | 8.050 |

Annexure – IV

| VEHICLE |
| --- |
| S.No | Description | Unit Cost | Qty | Total Cost | Total Cost in Million |
| 1 | Vehicle 1000cc | 2,100,000 | 1 | 2,100,000 | 2.100 |
| 2 | Registration of Vehicle | 100,000 | 1 | 100,000 | 0.100 |
|  | Sub Total |  |  | 2,200,000 | 2.200 |

Annexure – V

| OPERATIONAL EXPENDITURES |
| --- |
| S.No | Description | Total Cost (in Rs.) | Total Cost (in Million) |
| 1 | POL | 200,0000 | 2.000 |
| 2 | Other Service Rendered | 300,000 | 0.300 |
| 3 | Office Stationary | 20,0000 | 0.200 |
| 4 | Computer Stationary | 20,0000 | 0.200 |
| 5 | Contigencies | 20,0000 | 0.200 |
| 6 | Advertismenet/Publicity | 300000 | 0.300 |
| 7 | TA/DA | 200000 | 0.200 |
|  | Total | 3400,000 | 3.400 |

Annexure – VI

| RECURRING EXPENDITURES |
| --- |
| S.No | Description | Unit Cost | Qty | Total Cost / Month | Total Cost for 12 Months (in Rs.) | Total Cost for 12 Months (in Million) |
| 1 | Office Stationary | 5000 | 7 | 35000 | 420000 | 0.420 |
| 2 | Other Services Rendered | 5000 | 7 | 35000 | 420000 | 0.420 |
| 3 | Computer Stationary | 5000 | 7 | 35000 | 420000 | 0.420 |
| 4 | Internet WiFi USB | 5000 | 7 | 35000 | 420000 | 0.420 |
| 5 | POL for Vehicle | 50000 | 7 | 350000 | 4200000 | 4.200 |
| 6 | TA/DA | 20000 | 1 | 20000 | 240000 | 0.240 |
| 7 | Contigengies | 5000 | 7 | 35000 | 420000 | 0.420 |
|  | Total | 545000 | 6540000 | 6.540 |

Annexure-VII

| HUMAN RESOURCE |
| --- |
| S.No | Description | BPS | No of Posts | Pay per Month | Year 1 Salary | In Millions |
| 1 | Assistant Project Coordinator | 16 | 1 | 60000 | 720,000 | 0.720 |
| 2 | Interns | 10 | 07 | 25,000 | 2100000 | 2.100 |
| 3 | Driver | 5 | 1 | 20,000 | 240,000 | 0.240 |
|  | Sub Total |  | 09 | 105000 | 3060000 | 3.06 |

LIST OF MODEL SCIENCE LAB EQUIPMENTS

Note: Cost Break for each item has been included with current market survey without tax, Tax have been included in total Summary of Cost at Annexure.

| BIOLOGY |
| --- |
| S. # | Name of Apparatus | Quantity | Unit Price | Total Amount |
| 1 | Compound Microscope | 4 | 9,500 | 38,000 |
| 2 | Microscope Dissection | 5 | 4,000 | 20,000 |
| 3 | Magnifying Glasses | 10 | 250 | 2,500 |
| 4 | Dissection Box | 5 | 350 | 1,750 |
| 5 | Dissection Board/tray | 20 | 300 | 6,000 |
| 6 | Watch Glasses | 10 | 100 | 1,000 |
| 7 | Petri Dish Set | 10 | 150 | 1,500 |
| 8 | Beaker 100 ml | 10 | 100 | 1,000 |
| 9 | Beaker 400-500 ml | 2 | 200 | 400 |
| 10 | Beaker 1000 ml | 1 | 300 | 300 |
| 11 | Model of Human Skeleton | 1 | 4,000 | 4,000 |
| 12 | Model of Human Eye | 1 | 2,500 | 2,500 |
| 13 | Model of Human Heart | 1 | 1,800 | 1,800 |
| 14 | Model of Human Brain | 1 | 2,200 | 2,200 |
| 15 | Model of Human Kidney | 1 | 2,000 | 2,000 |
| 16 | Plain Slides (packets) | 10 | 1,500 | 15,000 |
| 17 | Cover slips (packets) | 10 | 500 | 5,000 |
| 18 | Dropper (Dozens) | 2 | 250 | 500 |
| 19 | Empty Jars for collection | 15 | 150 | 2,250 |
| 20 | Glass Funnels | 5 | 150 | 750 |
| 21 | Test tubes (packets) | 2 | 10 | 20 |
| 22 | Thermos flask | 2 | 1,100 | 2,200 |
| 23 | Thermometer | 5 | 120 | 600 |
| 27 | Glass Tubes(Kg) | 2 | 750 | 1,500 |
| 28 | Sprit lamps | 5 | 150 | 750 |
| 29 | Tripod | 5 | 150 | 750 |
| 30 | Iron Stand | 5 | 650 | 3,250 |
| 31 | Wire Gauze | 10 | 25 | 250 |
| 33 | Corks / Runner stopper | 25 | 20 | 500 |
| 35 | Disposable Syringes | 50 | 10 | 500 |
| 36 | Pipette 10 ml | 5 | 250 | 1,250 |
| 38 | Plastic Bags (grams) | 200 | 100 | 20,000 |
| 39 | Black Paper (Packets) | 2 | 100 | 200 |
| 40 | Filter Paper (Packets) | 5 | 650 | 3,250 |
| 41 | Blotting Paper (Packets | 5 | 650 | 3,250 |
| 42 | Drawing pins (Packets) | 2 | 50 | 100 |
| 43 | Paper pins (packets) | 5 | 50 | 250 |
| 44 | Nail 1 inch (grams) | 200 | 10 | 2,000 |
| 46 | Paper clips (packets) | 2 | 150 | 300 |
| 47 | Cellophane Membrane (packets) | 2 | 450 | 900 |
| 54 | Electronic balance | 1 | 1,500 | 1,500 |
| 55 | Cotton roll | 5 | 100 | 500 |
| 56 | Glycerin (litre) | 1 | 850 | 850 |
| 57 | Ethyl alcohol (litre | 1 | 1,100 | 1,100 |
| 58 | Formalin (Litre) | 1 | 350 | 350 |
| 59 | Sodium bicarbonate (Kg) | 2 | 200 | 400 |
| 60 | Potassium Hydroxide (Kg) | 2 | 400 | 800 |
| 61 | Iodine solution (Liter) | 1 | 650 | 650 |
| 62 | Starch (Kg) | 1 | 750 | 750 |
| 63 | Glucose (Kg) | 1 | 250 | 250 |
| 64 | Sodium Hydroxide (kg) | 2 | 250 | 500 |
| 65 | Copper sulphate (kg) | 2 | 450 | 900 |
| 66 | HCl (bottle) | 1 | 250 | 250 |
| 67 | H2SO4 (bottles) | 1 | 250 | 250 |
| 68 | Paraffin (bottle) | 1 | 150 | 150 |
| 69 | Vaseline (packet) | 1 | 250 | 250 |
| 70 | NaCl (packet) | 1 | 150 | 150 |
| 74 | Chloroform (bottle) | 1 | 650 | 650 |
| 75 | Methylated Spirit (liter) | 4 | 350 | 1,400 |
|  | TOTAL |  |  | 161,920 |

| Specimens in bottle |
| --- |
| S. # | Name of Apparatus | Quantity | Unit Price | Total Amount |
| 81 | sponge | 1 | 180 | 180 |
| 82 | jelly fish | 1 | 200 | 200 |
| 84 | hdra | 1 | 150 | 150 |
| 86 | tape warm | 1 | 150 | 150 |
| 87 | ascaris | 1 | 200 | 200 |
| 88 | leach | 1 | 200 | 200 |
| 89 | grass hopper/ spider | 1 | 150 | 150 |
| 90 | fresh water mussel | 1 | 150 | 150 |
| 91 | snail | 1 | 150 | 150 |
| 92 | star fish | 1 | 200 | 200 |
| 93 | Sea urchin | 1 | 200 | 200 |
| 95 | Dog Fish | 1 | 1,100 | 1,100 |
| 96 | toad | 1 | 150 | 150 |
| 98 | wall lizard | 1 | 150 | 150 |
| 100 | turtle | 1 | 1,250 | 1,250 |
| 101 | snake | 1 | 1,500 | 1,500 |
| 102 | scorpion | 1 | 350 | 350 |
| 103 | mushroom | 1 | 120 | 120 |
| 104 | cuttle fish | 1 | 450 | 450 |
| 105 | pigeon (stuffed) | 1 | 750 | 750 |
|  |  |  |  | 7,750 |

| prepared slides |
| --- |
| S. # | Name of Apparatus | Quantity | Unit Price | Total Amount |
| 106 | Bacteria | 1 | 120 | 120 |
| 107 | Rhizopus | 1 | 120 | 120 |
| 108 | Spirogyra | 1 | 120 | 120 |
| 109 | monocot stem | 1 | 120 | 120 |
| 110 | monocot root | 1 | 120 | 120 |
| 111 | monocot leaf | 1 | 120 | 120 |
| 112 | Dicot stem | 1 | 120 | 120 |
| 113 | Dicot root | 1 | 120 | 120 |
| 114 | Dicot leaf | 1 | 120 | 120 |
| 115 | Amoeba | 1 | 250 | 250 |
| 116 | Paramecium | 1 | 120 | 120 |
| 117 | Set of mitosis | 1 | 720 | 720 |
| 118 | set of Meiosis | 1 | 1,500 | 1,500 |
| 119 | leaf Epidermis | 1 | 120 | 120 |
| 120 | skin of animals | 1 | 950 | 950 |
| 121 | Muscular Tissues | 1 | 120 | 120 |
| 122 | Nervous tissues | 1 | 120 | 120 |
| 123 | Blood smear | 1 | 120 | 120 |
| 124 | yeast | 1 | 120 | 120 |
| 125 | chlamydomonas | 1 | 120 | 120 |
| 126 | volvax | 1 | 120 | 120 |
|  |  |  |  | 5,460 |
| Charts |
| S. # | Name of Apparatus | Quantity | Unit Price | Total Amount |
| 127 | Bacteria | 1 | 150 | 150 |
| 128 | funeria | 1 | 150 | 150 |
| 129 | ferns | 1 | 150 | 150 |
| 130 | Gymnosperm | 1 | 150 | 150 |
| 131 | Angiosperm | 1 | 150 | 150 |
| 132 | Paramecium | 1 | 150 | 150 |
| 133 | Article system of frog | 1 | 150 | 150 |
| 134 | Venus system of frog | 1 | 150 | 150 |
| 135 | reproductive system of frog | 1 | 150 | 150 |
| 136 | brain system of frog | 1 | 150 | 150 |
| 137 | Excretory system of frog | 1 | 150 | 150 |
| 138 | Digestive system of frog | 1 | 150 | 150 |
| 139 | Kidney system of frog | 1 | 150 | 150 |
| 140 | Human Ear | 1 | 150 | 150 |
| 141 | Structure of DNA | 1 | 150 | 150 |
| 142 | Stages of frog development | 1 | 150 | 150 |
| 143 | Bussia flower | 1 | 150 | 150 |
| 144 | germinating seed epigeal | 1 | 150 | 150 |
| 145 | germinating seed hypogeal | 1 | 150 | 150 |
| 146 | fruit5s | 1 | 150 | 150 |
| 147 | vegetables | 1 | 150 | 150 |
| 148 | birds | 1 | 150 | 150 |
| 149 | Animal | 1 | 150 | 150 |
|  |  |  |  | 3,450 |

| Chemistry |
| --- |
| S. # | Name of Apparatus | Quantity | Unit Price | Total Amount |
| 1 | Glass Tubbing | 20 | 750 | 15,000 |
| 2 | Triangular Flask | 6 | 150 | 900 |
| 3 | Spirit Lamp | 12 | 150 | 1,800 |
| 4 | Cork Bores | 6 | 250 | 1,500 |
| 5 | Cork (wooden, Rubber) | 50 | 20 | 1,000 |
| 6 | Flat bottom Flask | 12 | 150 | 1,800 |
| 7 | Physical Balance | 2 | 4,000 | 8,000 |
| 8 | Weight Box | 1 | 750 | 750 |
| 9 | Beakers (50 ml, 100ml, 500 ml) | 12 | 200 | 2,400 |
| 10 | Volumetric Flask | 12 | 150 | 1,800 |
| 11 | Graduated Cylinder | 6 | 200 | 1,200 |
| 13 | Burette | 6 | 550 | 3,300 |
| 14 | Pipette | 6 | 120 | 720 |
| 15 | Specific Gravity Bottle | 6 | 250 | 1,500 |
| 16 | Thermometer (Doctor) | 2 | 100 | 200 |
| 17 | Fusion Tube | 1 | 150 | 150 |
| 18 | Iron Stand | 6 | 650 | 3,900 |
| 19 | Wire Gauze | 12 | 25 | 300 |
| 20 | Stirrer | 12 | 65 | 780 |
| 21 | Burner | 6 | 450 | 2,700 |
| 22 | Tripod | 6 | 150 | 900 |
| 23 | Glass Rod | 12 | 65 | 780 |
| 24 | China Dish | 12 | 120 | 1,440 |
| 25 | Filter Paper | 6 | 650 | 3,900 |
| 26 | Glass Tube | 24 | 750 | 18,000 |
| 27 | Glass Tube Stand/ Rack | 6 | 150 | 900 |
| 28 | PH Paper | 3 | 150 | 450 |
| 29 | Litmus Paper | 6 | 50 | 300 |
| 30 | Dropper | 12 | 10 | 120 |
| 31 | Funnel | 12 | 150 | 1,800 |
| 40 | watch glass | 12 | 100 | 1,200 |
| 41 | Microscope | 2 | 9,500 | 19,000 |
| 42 | Glass Slide | 6 | 150 | 900 |
| 44 | Mortar | 6 | 450 | 2,700 |
| 45 | Test tube Holder | 12 | 65 | 780 |
| 46 | Wolf Bottle | 12 | 150 | 1,800 |
| 47 | Thistle Funnel | 6 | 100 | 600 |
| 48 | Glass Cylinder with cover | 12 | 200 | 2,400 |
| 49 | Beehive shelf | 6 | 150 | 900 |
| 50 | Trough | 12 | 250 | 3,000 |
| 51 | Round Bottom Flask | 12 | 150 | 1,800 |
| 52 | Flat Bottom Flask | 12 | 150 | 1,800 |
| 53 | Periodic Table | 2 | 500 | 1,000 |
|  |  |  |  | 116,170 |

| S. # | Name of Apparatus | Quantity | Unit Price | Total Amount |
| --- | --- | --- | --- | --- |
| 1 | Spirit | 5 | 350 | 1,750 |
| 2 | Naphthalene | 2 | 300 | 600 |
| 3 | Copper Sulphate | 1 | 450 | 450 |
| 5 | Potassium Sulphate | 1 | 300 | 300 |
| 6 | Aluminum Sulphate | 1 | 200 | 200 |
| 7 | Backing Soda | 1 | 200 | 200 |
| 8 | Washing Soda | 1 | 270 | 270 |
| 9 | Vinegar | 3 | 150 | 450 |
| 10 | Lime water | 2.5 | 150 | 375 |
| 11 | Sodium Hydroxide | 1 | 250 | 250 |
| 12 | Hydrochloric Acid | 5 | 250 | 1,250 |
| 13 | Sulphuric Acid | 5 | 250 | 1,250 |
| 14 | Nitric Acid | 5 | 250 | 1,250 |
| 15 | Oxalic Acid | 5 | 250 | 1,250 |
| 16 | potassium Hydroxide | 1 | 400 | 400 |
| 17 | Methyl Orange | 2 | 750 | 1,500 |
| 18 | Sodium Carbonate | 3 | 270 | 810 |
| 19 | Sodium Bicarbonate | 3 | 200 | 600 |
| 20 | Sodium Chloride | 3 | 150 | 450 |
| 21 | Ammonium Chloride | 3 | 180 | 540 |
| 22 | Benzene | 1 | 650 | 650 |
| 23 | Sulpher | 1 | 200 | 200 |
| 24 | Carbon Disulphate | 1 |  | 0 |
| 27 | Potassium Chlorate | 1 | 750 | 750 |
| 29 | Calcium Carbonate | 1 | 180 | 180 |
| 31 | Silver Nitrate | 1 | 3,600 | 3,600 |
| 32 | Ammonium Hydroxide | 3 | 150 | 450 |
| 33 | Calcium Hydroxide | 1 | 300 | 300 |
| 35 | Sodium Hydroxide | 1 | 250 | 250 |
| 37 | Sodium Iodide Solution | 1 | 2,000 | 2,000 |
| 38 | Iron Sulphate | 1 | 200 | 200 |
|  |  |  |  | 22,725 |

| Physics |
| --- |
| S. # | Name of Apparatus | Quantity | Unit Price | Total Amount |
| 1 | Veriner Caliper | 3 | 650 | 1,950 |
| 2 | Solid Cylinder ( Diff Sizes) | 3 | 150 | 450 |
| 3 | Screw Gauge | 3 | 650 | 1,950 |
| 4 | Wire of Diff Sizes | 1 | 550 | 550 |
| 5 | Angle iron 2 meter long | 3 | 950 | 2,850 |
| 6 | v-shaped iron stand | 3 | 150 | 450 |
| 7 | steel bolt | 3 | 50 | 150 |
| 8 | stop watch | 3 | 350 | 1,050 |
| 9 | set square | 3 | 1,000 | 3,000 |
| 10 | Free Fall Apparatus | 3 | 1,100 | 3,300 |
| 11 | Metallic Ball with Hook | 3 | 150 | 450 |
| 13 | Plumb Line | 3 | 65 | 195 |
| 16 | Weight Box | 1 | 750 | 750 |
| 17 | Wooden Block | 6 | 65 | 390 |
| 18 | Spring Balance | 3 | 250 | 750 |
| 19 | Pan | 6 | 65 | 390 |
| 20 | Meter Rod (100 cm, 50 cm) | 3 | 120 | 360 |
| 21 | Gravesend Apparatus | 2 | 950 | 1,900 |
| 22 | slotted weights with hanger | 2 | 250 | 500 |
| 23 | Drawing pin | 12 |  | 0 |
| 24 | wooden wedge | 12 | 90 | 1,080 |
| 25 | inclined plane with frictionless pulley | 3 | 650 | 1,950 |
| 26 | brass rod | 6 | 250 | 1,500 |
| 27 | single fixed pulley | 3 | 120 | 360 |
| 28 | iron stand | 3 | 650 | 1,950 |
| 29 | helical spring apparatus complete set with sollred weights | 3 | 650 | 1,950 |
| 30 | Physical balance | 1 | 4,000 | 4,000 |
| 31 | electronic balance | 1 | 1,500 | 1,500 |
| 32 | beaker 100, 50, 25cc | 12 | 100 | 1,200 |
| 33 | thermometer centigrade | 6 | 120 | 720 |
| 34 | small wooden bench | 6 | 50 | 300 |
| 35 | calorimeter with stirrer | 3 | 450 | 1,350 |
| 36 | hypsometer | 3 | 450 | 1,350 |
| 37 | Lead shot | 3 | 250 | 750 |
| 38 | Sprit lamp | 6 | 150 | 900 |
| 39 | Tropot iron stand | 3 | 150 | 450 |
| 40 | Resonance tube apparatus | 3 | 1,100 | 3,300 |
| 41 | tuning forks complete set | 3 | 4,800 | 14,400 |
| 43 | concave mirror | 12 | 100 | 1,200 |
| 44 | optical bench complete set | 3 | 1,100 | 3,300 |
| 47 | drawing boards | 6 | 150 | 900 |
| 50 | protector | 3 | 200 | 600 |
| 51 | set square | 3 | 950 | 2,850 |
| 52 | concave mirror of large focal length (10-20 cm) | 6 | 100 | 600 |
| 53 | meter rod stand | 3 | 120 | 360 |
| 54 | prism | 3 | 90 | 270 |
| 55 | voltmeter | 3 | 650 | 1,950 |
| 56 | ammeter | 3 | 650 | 1,950 |
| 57 | Galvanometer | 3 | 650 | 1,950 |
| 58 | Micro Ammeter | 3 | 1,800 | 5,400 |
| 59 | Milli Ammeter | 3 | 1,800 | 5,400 |
| 60 | Micro Voltmeter | 3 | 1,800 | 5,400 |
| 61 | Milli voltmeter | 3 | 1,800 | 5,400 |
| 62 | keys | 12 | 65 | 780 |
| 63 | Battery 6 volt china | 3 | 750 | 2,250 |
| 64 | rheostate | 1 | 950 | 950 |
| 65 | resisters (5 0hm - 100 ohm) | 24 | 40 | 960 |
| 66 | high resistance box (1-5000 ohm) | 2 | 1,500 | 3,000 |
| 67 | fractional (low resistance) 0.1-50 ohm) | 6 | 2,500 | 15,000 |
| 68 | connecting wire | 30 | 150 | 4,500 |
| 69 | bar magnet | 6 | 250 | 1,500 |
| 70 | compass | 6 | 120 | 720 |
| 71 | circular coi apparatus | 3 | 950 | 2,850 |
| 72 | power supply (15 volt DC) | 2 | 2,500 | 5,000 |
| 73 | Semi conductor diode | 3 | 2,000 | 6,000 |
| 74 | Milli Ammeter | 3 | 650 | 1,950 |
| 75 | AND Gate 7408 | 6 | 450 | 2,700 |
| 76 | OR gate (7432) | 6 | 450 | 2,700 |
| 77 | LED indicator | 6 | 450 | 2,700 |
| 78 | NOT Gate 7405 | 6 | 450 | 2,700 |
| 79 | NAND gate 7400 | 6 | 450 | 2,700 |
| 80 | Buzzer Unit | 6 | 450 | 2,700 |
| 81 | PNP, NPN Transistor | 6 | 20 | 120 |
| 82 | Multimeter Digital China | 3 | 750 | 2,250 |
|  |  |  |  | 161,955 |

ANNEXURE – IX

| PROJECT MANAGEMENT PLAN |
| --- |
| S. No | Activities | Implementation Plan Months |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| 1 | PC1 Approval & Fund Release |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Approval of PC1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Fund Allocation & Releases |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Renovation Work |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Finalization of List of Schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Procurement of Goods & Services |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Capital |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Tendering of RFP's |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Shortlisting & Finalization of Companies / Firms |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 | Award of Contracts |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Recurring |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 | Tendering of RFP's |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5 | Shortlisting & Finalization of Companies / Firms |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.6 | Award of Contracts |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Supply & deployment of Hardware / IT Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Delivery of Model Science Labs Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | HR Hiring CIU Team |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Hiring of Required team only |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Training of Resources |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Resource Trainings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Monitoring of the Project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 | Monitoring of the project |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Safety Rules for Teachers

Following points are highly recommended for providing a healthy and safe environment during practical activities:

- It is highly recommended that a school should develop a Safety Checklist and establish regular inspection schedules and procedures for checking safety

and first-aid equipment.

- Install fire extinguisher(s), sand bucket(s) and fire blanket(s) in easily accessible locations (general rule to follow is that the accessibility of these items should be within 15 seconds or 30 steps from any location in the

room). Restock these safety equipment as per need (upon expiry or after usage) and train teachers and students to use them when required.

- Keep a first-aid box (including bandage tape, gauze, antiseptic, scissors, cotton wool, etc.) in the laboratory.

- Make certain that the teachers and students wear adequate protective equipment, including laboratory coats, safety goggles and gloves, when experiments are conducted.

- Clearly mark fire exits, and keep exits unobstructed.

- Display and follow safety signs. (See Annexure B)

- Keep water, gas and electricity turned off when not in use.

- Chemical shelving should be wooden, with a front lip and ventilated.

- Store flammables and corrosives chemicals separately in suitable cabinets.

- Do not store flammable liquids in open containers.

- Make an appropriate system for waste disposal.

- Make certain that too many appliances are not plugged into one outlet/ socket.

- Avoid frayed electrical cords or placing electric cords under rugs or near heat sources.

- The filters in the fume cupboard should be changed at regular intervals.

# Safety Rules for Students

Implementing proper laboratory safety procedures as part of instructions reduces the possibility of a teacher or student suffering from an incident or injury. Also, it helps to minimise the losses resulting from accidents and promotes a safe approach in students.

Given is the list of laboratory safety rules recommended to be followed at all times by the students:

- Conduct yourself in a responsible manner at all times in the laboratory. Practical jokes, pranks and horseplay are strictly prohibited.

- When entering a science laboratory, avoid touching any equipment, chemicals, electrical and electronic devices, or other materials until you are instructed to do so.

- Follow all written and verbal instructions carefully given by the teacher/ instructor.

- Do not start any practical work unless you are clear about its directions. Ask your teacher before proceeding with the activity.

- Wear a laboratory coat, safety goggles and gloves at all times in the laboratory.

- Keep your working station clean and tidy.

- Do not eat or drink in the laboratory.

- Be cautious at all times in the laboratory. Call the teacher immediately if you notice any risky conditions.

- Never work alone in the laboratory. PRESENCE OF A TEACHER OR SUPERVISOR IS NECESSARY.

- Bring only the laboratory instructions and notebook into the laboratory. Other materials (purse, bags, etc.) should be placed outside the laboratory.

- Read the labels and instructions on the chemicals and electronic devices carefully before use.

- Keep your hands away from eyes and mouth while using chemicals.

- Know the locations and operating procedures of all safety equipment, including a first-aid kit, fire extinguisher and fire alarm.

- Do not place combustibles (paper/ notebooks) near heat source.

- Do not wear contact lenses in the laboratory.

- In case of any spillage, breakage or injury, report to the teacher instantly. STAY CALM.

- If a chemical splashes into your eyes or skin, flush your eyes with running water thoroughly and seek medical attention.

- Examine glassware before use. Never use chipped, cracked or dirty glassware.

- Do not taste or smell any chemical present in the laboratory.

- When recording an observation, keep yourself at least one foot away from the setup.

- Take great care when transferring acid and other corrosive chemicals from one apparatus to another. Hold the apparatus securely as demonstrated by the teacher.

- When removing an electrical plug from its socket, switch off and grasp the plug, not the electrical cord. Hands must be dry when touching an electrical

switch, plug or outlet/ socket.

- Never return unused chemical to its original container.

- Do not take any chemical away from the laboratory premises.

- It is recommended to avoid mouth pipetting. Direcorate encourages schools/ colleges to use rubber pipette filler. However, if mouth pipetting is done, it should be carried out under a teacher’s supervision.

- Do not immerse hot glassware in cold water as the glassware may break. Put the heated glassware at a separate place to be cooled.

- Never look into a container that is being heated. Always observe containers from sideways.

- If the Bunsen burner goes out accidentally, immediately turn off the control device/ gas supply.

- Never leave a lit burner unattended.

- While heating a chemical in a test tube, do not point the mouth of the test tube towards yourself or anyone else.

- Wash your hands with liquid soap and water on leaving the laboratory.